## BugzillaReport_10.6.2014.csv
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
51 | Fall_2014_Team03 | FED | bvanover@usc.edu | VERIFIED | FIXED | Devise Risk Mitigation Plan for Mobile Inexperience | 2014-09-28 22:39
53 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Identify a third-party transaction management tool | 2014-09-28 16:40
63 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Identify backend server tools/languages | 2014-09-23 11:43
102 | Fall_2014_Team03 | FED | bvanover@usc.edu | VERIFIED | FIXED | Geolocation Prototype | 2014-10-06 19:22
202 | Fall_2014_Team03 | OCD | apatni@usc.edu | CONFIRMED | --- | OCD Draft | 2014-10-06 19:19
204 | Fall_2014_Team03 | LCP | desiraju@usc.edu | CONFIRMED | --- | LCP | 2014-10-06 19:24
205 | Fall_2014_Team03 | FED | xiaotinb@usc.edu | CONFIRMED | --- | FED | 2014-10-06 19:25
206 | Fall_2014_Team03 | Architecture Description | ditongdi@usc.edu | CONFIRMED | --- | SSAD | 2014-10-06 19:29
37 | Fall_2014_Team03 | Project Website | bvanover@usc.edu | VERIFIED | FIXED | Publish Team Website | 2014-09-23 19:34
65 | Fall_2014_Team03 | OCD | xiaotinb@usc.edu | VERIFIED | FIXED | Generate Program Model | 2014-09-24 16:26
90 | Fall_2014_Team03 | LCP | desiraju@usc.edu | VERIFIED | FIXED | Valuation Commitment Package | 2014-09-29 20:59
103 | Fall_2014_Team03 | FED | xiaotinb@usc.edu | VERIFIED | FIXED | Prototype Presentation 10/2/2014 | 2014-10-06 19:22
48 | Fall_2014_Team03 | Non-component activity | apatni@usc.edu | VERIFIED | FIXED | Client Interaction Report | 2014-09-23 11:40
58 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | CONFIRMED | --- | Schedule, plan, and deliver Git tutorial to team | 2014-09-24 22:33
64 | Fall_2014_Team03 | OCD | ditongdi@usc.edu | VERIFIED | FIXED | Generate result chain | 2014-09-23 19:36
67 | Fall_2014_Team03 | Non-component activity | desiraju@usc.edu | VERIFIED | FIXED | Microsoft Project Plan - Week 02 | 2014-09-23 19:36
92 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/24/2014 (WinWin Negotiations #1) | 2014-09-24 23:00
141 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Week 4 PR/MPP | 2014-10-01 21:53
203 | Fall_2014_Team03 | Architecture Description | ditongdi@usc.edu | CONFIRMED | --- | Document Prototype | 2014-10-06 19:22
34 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/12/2014 | 2014-09-22 19:08
35 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/16/2014 | 2014-09-23 19:33
36 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Developer Meeting 9/18/2014 | 2014-09-23 19:34
40 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Generate Progress Report 9/17/2014 | 2014-09-23 19:35
87 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Developer Meeting 9/23/2014 | 2014-09-24 21:19
207 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Generate Bugzilla Report 9/28 - 10/5 | 2014-10-06 20:10
86 | Fall_2014_Team03 | OCD | apatni@usc.edu | VERIFIED | FIXED | Update Program Model, per the WinWin Discussion | 2014-10-01 21:50
133 | Fall_2014_Team03 | Non-component activity | ditongdi@usc.edu | VERIFIED | FIXED | Update Team Website | 2014-09-28 13:12
89 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | WONTFIX | PR Updates per TA Feedback | 2014-10-01 21:51
101 | Fall_2014_Team03 | Architecture Description | ditongdi@usc.edu | VERIFIED | FIXED | Individual Workflow Visions | 2014-09-29 21:06
173 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/30/2014 (WinWin Negotiations #2) | 2014-10-06 19:13
50 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Setup Remote Communication Protocol | 2014-09-23 11:41
100 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Developer Meeting 9/25/2014 | 2014-09-25 23:51
52 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | WinWin Negotiation Meeting | 2014-09-24 21:18
54 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Create Git repositories for development code | 2014-09-25 17:51
91 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Team Prototype Presentation | 2014-10-06 19:10