## Non-Component Activity
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
34 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/12/2014 | 2014-09-22 19:08
35 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Client Meeting 9/16/2014 | 2014-09-22 21:11
36 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Developer Meeting 9/18/2014 | 2014-09-22 19:09
40 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Generate Progress Report 9/17/2014 | 2014-09-22 19:10
48 | Fall_2014_Team03 | Non-component activity | apatni@usc.edu | VERIFIED | FIXED | Client Interaction Report | 2014-09-22 19:14
58 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | CONFIRMED | --- | Schedule, plan, and deliver Git tutorial to team | 2014-09-22 20:44
67 | Fall_2014_Team03 | Non-component activity | desiraju@usc.edu | VERIFIED | FIXED | Microsoft Project Plan - Week 02 | 2014-09-22 22:45
50 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | VERIFIED | FIXED | Setup Remote Communication Protocol | 2014-09-22 19:25
52 | Fall_2014_Team03 | Non-component activity | bvanover@usc.edu | IN_PROGRESS | --- | WinWin Negotiation Meeting | 2014-09-22 20:09

## Server
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
53 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Identify a third-party transaction management tool | 2014-09-22 20:20
63 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Identify backend server tools/languages | 2014-09-22 20:58
54 | Fall_2014_Team03 | Server | karcher@usc.edu | CONFIRMED | --- | Create Git repositories for development code | 2014-09-22 20:49

## FED
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
51 | Fall_2014_Team03 | FED | bvanover@usc.edu | CONFIRMED | --- | Devise Risk Mitigation Plan for Mobile Inexperience | 2014-09-22 19:29

## OCD
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
65 | Fall_2014_Team03 | OCD | xiaotinb@usc.edu | VERIFIED | FIXED | Generate Program Model | 2014-09-22 22:16
64 | Fall_2014_Team03 | OCD | ditongdi@usc.edu | VERIFIED | FIXED | Generate result chain | 2014-09-22 21:55

## Project Website
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed
37 | Fall_2014_Team03 | Project Website | bvanover@usc.edu | VERIFIED | FIXED | Publish Team Website | 2014-09-22 19:09